## Comm Plan Template
Project Plant Pals: Hiring Day Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Daily Stand-Up | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track
Facilities | Planning Meeting | Weekly | An Administrative Coordinator | Monday at 1pm | Phone call | Reserve rooms/spaces
Print Shop | Planning Check-in | Weekly | An Administrative Coordinator | Tuesday at 1pm | Phone call | Coordinate printed materials/signage
Volunteers | Planning Check-in | Weekly | Training Manager | Wednesday at 1pm | Email (from individual address) | Coordinate with volunteers and send reminders
HR | Planning Meeting | Daily | A Human Resources Specialist | Monday to friday at 9am | In Person | Check in on planning progress, provide support to department
Your Office Green Manager | Project Update | Weekly | Project Manager | Monday at 2pm | In Person | Update on event planning, ask questions, and get feedback
Candidates | Informational update | Weekly | A Human Resources Specialist | Monday at 1pm | Email (from company address) | Communicate schedule, location, and other necessary event details
Volunteers | Training | One time | A Training Manager | Thursday before the event | Phone call | Train volunteers to check-in and welcome candidates and direct the flow of traffic during the event
Catering | Planning Check-in | Weekly | An Administrative Coordinator | Friday at 1 pm | Phone call | Coordinate coffee service/snacks for candidates and lunch for HR
Senior Leadership | Project Update | One time | Project Manager | Debrief after the event | Email | High-level information and general updates

## Comm Plan Template 2 (hidden)
Project Communication Plan
Project Title:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliverable Info (What) | Recipient(s) (Who) | Delivery Method(s) (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information
Project Status
Agenda Minutes
Timeline Update
Project Updates Action Item Status
Project Risks

## Comm Plan Template 3 (hidden)
| Purpose | Medium | Frequency | Audience
Kickoff meeting
Project team meetings
Check-ins/ meeting recap
Project status meetings
UX design reviews