## Dashboard
Project Name: Project Plant Pals
Description: Project Plan
Owner: Matt, Project Manager
Status: Draft
Key Docs | Description
Project charter | Outline of the project
Statement of work | Lists of Work to be completed
Risk management plan | Outline of possible risks and paln on how to mitigate them
Schedule | Milestones and Risks
Budget | It contains the target budget
Communication plan | What, who, and how to communicate to
Shared folder | Folder to be used
RACI chart | Responsible, Accountable

## Project Schedule
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 1/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Hire delivery drivers | Human Resources Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate the delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Set up the software systems for tracking inventory management and fulfillment | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Oversee the installation of the fulfillment equipment | Inventory Manager | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Establish safety protocols and practices for the equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop a communication plan | Human Resources Specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Develop the employee training program | Human Resources Specialist | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Train Office Green employees to use the software and equipment | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 64000 | 0 | 64000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks |  |  |  | 15000 | 2 |  | 30000 |  | -30000
Task 2: Source packaging materials |  |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | two delivery drivers | 80 | 30 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source vendor | [5 empty] | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program
Task 1: Develop a communication plan for employees | HR specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Develop an employee training program | HR specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 3: Train Office Green employees | training manager | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 10000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 64000 | 0

## Communication Plan
Project Plant Pals: Hiring Day Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Daily Stand-Up | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track
Facilities | Planning Meeting | Weekly | An Administrative Coordinator | Monday at 1pm | Phone call | Reserve rooms/spaces
Print Shop | Planning Check-in | Weekly | An Administrative Coordinator | Tuesday at 1pm | Phone call | Coordinate printed materials/signage
Volunteers | Planning Check-in | Weekly | Training Manager | Wednesday at 1pm | Email (from individual address) | Coordinate with volunteers and send reminders
HR | Planning Meeting | Daily | A Human Resources Specialist | Monday to friday at 9am | In Person | Check in on planning progress, provide support to department
Your Office Green Manager | Project Update | Weekly | Project Manager | Monday at 2pm | In Person | Update on event planning, ask questions, and get feedback
Candidates | Informational update | Weekly | A Human Resources Specialist | Monday at 1pm | Email (from company address) | Communicate schedule, location, and other necessary event details
Volunteers | Training | One time | A Training Manager | Thursday before the event | Phone call | Train volunteers to check-in and welcome candidates and direct the flow of traffic during the event
Catering | Planning Check-in | Weekly | An Administrative Coordinator | Friday at 1 pm | Phone call | Coordinate coffee service/snacks for candidates and lunch for HR
Senior Leadership | Project Update | One time | Project Manager | Debrief after the event | Email | High-level information and general updates