## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action. |  |  |  | AMBER
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
purchased a new software to keep track of incoming orders and installed it | June 15 | Completed | Software Enginner |  | The installation took three days longer than expected.
Began sending first test batch of Plant Pals orders to customers | June 21 | Completed | Fulfillment Director |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | July 7 | Upcoming | Software Enginner |  | The newsletter must follow Office Green’s brand design guidelines.
Hit at least 95% of delivery dates on time | July 19 | Upcoming | Fullfillment Director |  | The error rate should be under 5%.
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
The warehouse team reports that 10% of the plants were not properly potted. |  | Profit loss, complaints, and budget issues | Assess the situation and improve plant potting process |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software |  |  | Software Engineer
The current delivery completion rate is 80% |  | Cancelled subscriptions | Hire and train more delivery drivers |  |  | HR Specialist